## System and Flows
System and Scope
Overview | Scope | Inputs | Outputs | Ownership | Supervisor
LLM-Powered Incident response Assistant for SMEs: Ingests network logs from IDS, passes it to LLM for summarisation, Outputs into a DB, Displays on a Web Dashboard. | Local Deployment on VM for testing., evaluates how LLMs can assist SMEs during incident response. | JSON logs | LLM-generated dashboard data. | Matthew Fish | Nathan Clarke
Data Flow
Source | Type | Flow | PII Risk | Notes
Network logs | Structured JSON | JSON Network logs to LLM | Low–Medium | IP addresses may indirectly identify individuals.
LLM | JSON input/ Text output | Receives JSON, Returns summarised data | Low | Model runs locally so no external data transfer.
Database | Structured | Stores processes data | Medium | Must ensure encryption and restricted access.
Web dashboard | Structured | Displays processed data | Low | User authentication needed to prevent exposure.
Test VMs | Unstructured | Simulated attacks | None

## Risk Categories and Impact
Potential Risk Categories |  | Likelihood and Impact |  |  |  |  | Rules
Category | Description | Risk | Likelihood | Impact | Overall Risk | Rationale | 1 to 10 | Low, Medium, High, Significant
Bias & Fairness | LLM may dramatise risk scores. | Model bias in classification | 5 | 7 | High | Depends on the data the LLM has been trained with. Will use a RAG to reduce bias as much as possible.
Privacy Violations | Logs could contain identifiable IPs or metadata. | Privacy leak via IP data | 4 | 8 | High | Rare but could have a serious impact. Will try to anonymise IPs where possible.
Explainability | LLM output may be unclear or untraceable to specific log evidence. | Model hallucination / misinterpretation | 5 | 7 | High | Will implement a way to check the processed data.
Security | Exposure of database, API endpoints, or LLM prompt injection, User tampering. | Database compromise | 2 | 10 | Medium | Huge affect on the company as an attacker could do a ransomware attack or use the logs for other attacks.
Regulatory / Compliance | Data handling must align with GDPR. | LLM prompt injection or misuse | 2 | 7 | Medium | Stored locally so very unlikely and an implemented check on the data would help with security and outputs.
Operational / Reliability | LLM, IDS, API or Dashboard downtime may stop attacks from being prevented. | Unauthorised access to dashboard, llm or IDS | 2 | 10 | Medium/High | Will all be deployed locally and auth access will be required for dashboard. Access controls would be implemented for only admin to access llm or IDS.
Data Integrity | Corrupted or manipulated logs could cause false insights. | Data loss / corruption | 2 | 5 | Medium | Could use backups of data but requires further storage and security.
|  | System downtime | 5 | 8 | High | Downtime for updates, internet loss, power loss affects the whole system.
|  | Non-compliance with GDPR and computer misuse for users | 2 | 10 | Medium | Implment secure handling of data, access controls and systems in place to prevent tool being misused.

## Existing Mitigation Control
Existing Mitigation Control
Control | Description | Effectiveness | Enforced? | Works as intended?
Docker container isolation | Each service runs in its own container. | High | Planned | To be Verified
Everything run locally | No public exposure to data. | High | Planned | To be Verified
Basic auth on API/dashboard | Restricts access. | Medium | Planned | To be Tested
Access Control to system and tools (IDS/LLM) | Restricts access. | Medium | Planned. Would need to be enforced on company host. | To be Tested
Pseudonymisation of IPs | Truncate or hash IP addresses. | Medium | Planned for storing and transmission in DB. Most likely will need it displayed on dashboard. | To be Tested
Database user roles | Least-privilege accounts. | Medium | Planned | To be tested
System updates | Patch Docker images regularly, IDS, LLM, Python. | High | Ongoing | Yes

## Risk Register
Risk Register
Risk Description | Likelihood | Impact | Overall Risk | Controls | Owner | Mitigation / Plan | Timeline
LLM produces biased or inconsistent summaries | 5 | 7 | High | Will review it manually. | Matthew | Validate LLM outputs vs. known threats. RAG | By Feb
IP data exposes personal info | 4 | 8 | High | IP anonymisation, stored locally. | Matthew | Hash Ips | Jan
Unauthorised LLM, IDS or dashboard access | 2 | 10 | Medium | Auth / Access Controls | Matthew | Implement JWT/API-key login. Access controls locally. | Jan
DB compromise | 2 | 10 | Medium | Auth / Access Controls | Matthew | Only Admin login. | Feb
Prompt injection or malicious input | 2 | 7 | Medium | Sanitise model inputs. | Matthew | Validate all logs before / after LLM processing | Jan
Data loss | 2 | 5 | Medium | Backups | Matthew | Backups | Feb
Downtime or service failure | 5 | 8 | High | Monitoring. | Matthew | Monitor uptime, add healthchecks, updates scheduled a low volume times. | Feb
Non-compliance with GDPR / Computer Misuse | 2 | 10 | Medium | Ethical review. | Matthew | Document compliance steps. | Ongoing