## System and Flows
System and Scope
Overview | Scope | Inputs | Outputs | Ownership | Supervisor
LLM-Powered Incident response Assistant for SMEs: Ingests network logs from IDS, passes it to LLM for summarisation, Outputs into a DB, Displays on a Web Dashboard. | Local Deployment on VM for testing., evaluates how LLMs can assist SMEs during incident response. | JSON logs | LLM-generated dashboard data. | Matthew Fish | Nathan Clarke
Data Flow
Source | Type | Flow | PII Risk | Notes
Network logs | Structured JSON | JSON Network logs to LLM | Low–Medium | IP addresses may indirectly identify individuals.
LLM | JSON input/ Text output | Receives JSON, Returns summarised data | Low | Model runs locally so no external data transfer.
Database | Structured | Stores processes data | Medium | Must ensure encryption and restricted access.
Web dashboard | Structured | Displays processed data | Low | User authentication needed to prevent exposure.
Test VMs | Unstructured | Simulated attacks | None | Used for testing only

## Risk Categories and Impact
Potential Risk Categories |  | Likelihood and Impact |  |  |  |  | Rules
Category | Description | Risk | Likelihood | Impact | Overall Risk | Rationale | 1 to 10 | Low, Medium, High, Significant
Bias & Fairness | LLM may dramatise risk scores. | Model bias in classification | 5 | 7 | High | Depends on the data the LLM has been trained with. Will use a RAG to reduce bias as much as possible.
Privacy Violations | Logs could contain identifiable IPs or metadata. | Privacy leak via IP data | 4 | 8 | High | Rare but could have a serious impact. Will try to anonymise IPs where possible.
Explainability | LLM output may be unclear or untraceable to specific log evidence. | Model hallucination / misinterpretation | 5 | 7 | High | Will implement a way to check the processed data.
Security | Exposure of database, API endpoints, or LLM prompt injection, User tampering. | Database compromise | 2 | 10 | Medium | Huge affect on the company as an attacker could do a ransomware attack or use the logs for other attacks.
Regulatory / Compliance | Data handling must align with GDPR. | LLM prompt injection or misuse | 2 | 7 | Medium | Stored locally so very unlikely and an implemented check on the data would help with security and outputs.
Operational / Reliability | LLM, IDS, API or Dashboard downtime may stop attacks from being prevented. | Unauthorised access to dashboard, llm or IDS | 2 | 10 | Medium/High | Will all be deployed locally and auth access will be required for dashboard. Access controls would be implemented for only admin to access llm or IDS.
Data Integrity | Corrupted or manipulated logs could cause false insights. | Data loss / corruption | 2 | 5 | Medium | Could use backups of data but requires further storage and security.
Supply Chain | Third party risks (docker images, pre-trained LLM) | System downtime | 5 | 8 | High | Downtime for updates, internet loss, power loss affects the whole system.
People | Lack of user training and lack of incident response plan for if the tool got compromised | Non-compliance with GDPR and computer misuse for users | 2 | 10 | Medium | Implment secure handling of data, access controls and systems in place to prevent tool being misused.
|  | Supply chain risks | 4 | 6 | High | Dependencies on third-party vendors or libraries could fail or be compromised, affecting system stability and security.
|  | Insufficient Logging | 3 | 6 | Medium | Limited logging makes it harder to detect, investigate, or respond to issues
|  | User Error or misconfig | 4 | 5 | Medium | Misconfigurations or mistakes by users can cause outages or security issues
|  | Ethical Misuse of tools | 2 | 8 | Medium | Tools could be used unethically (e.g., privacy violations)

## Existing Mitigation Control
Existing Mitigation Control
Control | Description | Effectiveness | Enforced? | Works as intended?
Docker container isolation | Each service runs in its own container. | High | To be configured | To be Verified
Everything run locally | No public exposure to data. | High | To be configured | To be Verified
Basic auth on API/dashboard | Restricts access. | Medium | To be configured | To be Tested
Access Control | RBAC for system access. Principle of least pivilege. | Medium | To be configured | To be Tested
Pseudonymisation of IPs | Truncate or hash IP addresses before storing. | Medium | To be configured | To be Tested
Database Security | Least-privilege accounts , encryption at rest | Medium | To be configured | To be tested
System updates | Patch Docker images regularly, IDS, LLM, Python. | High | Ongoing | Yes
Input Sanitisation and validation | Validate and sanitise all logs before entering LLM. | Medium | To be configured | To be verified
Logging and monitoring | System healthchecks and logs for user actions. | Medium | To be configured | To be Verified
Backup and Recovery | Regular backups of database and critical files | High | To be configured | To be Verified

## Risk Register
Risk Register
Risk Description | Likelihood | Impact | Overall Risk | Controls | Owner | Mitigation / Plan | Timeline
LLM produces biased or inconsistent summaries | 5 | 7 | High | Will review it manually. | Matthew | Validate LLM outputs vs. known threats. RAG | By Feb
IP data exposes personal info | 4 | 8 | High | IP anonymisation, stored locally. | Matthew | Hash Ips | Jan
Unauthorised LLM, IDS, dashboard, db access | 2 | 10 | High | Auth / Access Controls,docker isolation | Matthew | Implement JWT/API-key login. Access controls locally. | Jan
Prompt injection or malicious input | 2 | 7 | Medium | Sanitise model inputs. | Matthew | Validate all logs before / after LLM processing | Jan
Data loss or corruption | 2 | 5 | Medium | Backups | Matthew | Backups | Feb
Downtime or service failure | 5 | 8 | High | Monitoring, healthchecks | Matthew | Monitor uptime, add healthchecks, updates scheduled at low volume times. | Feb
Non-compliance with GDPR / Computer Misuse | 2 | 10 | Medium | Ethical review, documentation | Matthew | Ethical review, Document compliance steps. | Ongoing
Supply chain risks | 4 | 6 | High | System updates, vulnerability scanning | Matthew | Trusted docker images, regular scans. | Ongoing
Insufficient Logging | 3 | 6 | Medium | Audit Logging | Matthew | Limited logging makes it harder to detect, investigate, or respond to issues. Access to tools are logged to a secure separate location | Ongoing
User Error or misconfig | 4 | 5 | Medium | Training and documentation | Matthew | Clear documentation for setup and use. Configuration to avoid manual errors. | Ongoing
Ethical Misuse of tools | 2 | 8 | Medium | Access controls, policies | Matthew | Restrict tool access to authorised users. Define and communicate acceptable use policy | Ongoing